## Sheet1
Project Type | Store Number | Address | City | State | DMA ID | DMA | RED | CM | A&E | RVP | Principal Partner | Status | Open Store | Project Status | Project Status | # of tablets per store | Equipment Vendor | Ship Date | Revisit Date | Scheduled Install Date | Installation Vendor | Install Status
RELOCATION | 11200 | 461 Columbia Ave | Lexington | SC | 546 | COLUMBIA SC | Michael Landru | Kevin Dalpiaz | ANE ABCD | RVP | ABC Franchise Changed | 2022-02-01 | 2023-01-15 | Under Construction | Under Construction | 3 | ABCD | 2023-01-15 | 2023-01-15 | 2023-01-15 | ABCD | Done
NEW | 11201 | 2812 School Street | Needville | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  | Linda Wiseley | FLENCHER, BENJAMIN | 2022-06-01 | 2023-01-18 | Under Construction | Under Construction | 4 | DDD | 2023-01-15 | 2023-01-15 | 2023-01-15 | XXX | Complete
ServerHandheld | 11202 | 5227 Decker Ln | Austin | TX | 635 | AUSTIN TX | Jon Brannin | Nick Rice |  | Linda Wiseley | REEDER RATLIFF | 2022-03-09 | 2023-01-24 | Under Construction | Under Construction | 1 | EEE | 2023-01-15 | 2023-01-15 | 2023-01-15 | ASSA | Finish
Audio | 11203 | 108 N Lincoln Dr (temp) | Troy | MO | 609 | ST. LOUIS MO | Michael Dee | Nick Rice |  |  | UMSTATTD, KEVIN | 2022-09-15 | 2023-01-24 | Under Construction | Under Construction | 2 | GGG | 2023-01-15 | 2023-01-15 | 2023-01-15 | ABCD | Start