## Sheet1
Project Type | Store Number | Address | City | State | DMA ID | DMA | RED | CM | A&E | RVP | Principal Partner | Status | Open Store | Project Status | # of tablets per store | Equipment Vendor | Ship Date | Revisit Date | Scheduled Install Date | Installation Vendor | Install Status
Server Handheld | 111 | 12901 Shelbyville Rd. | Middletown | KY | 529 | LOUISVILLE | Michael Dee | Nick Rice |  | Bobby Jones | ROGERS, DARRELL L. | 2023-09-06 | 2026-11-13 | Early Stage | 3 | EquipmentVendor |  |  |  | instalUser | Not Required
Server Handheld | 222 | 4287 S 144th St. | Omaha | NE | 652 | OMAHA | Michael Dee | Julieann Chism | Christina Hernandez |  | ESCH, INC. | 2023-05-28 |  | Plans Started | 4 | EquipmentVendor | 2023-10-07 | 2023-10-06 | 2023-10-02 | NVendor | Bbw stat2
Server Handheld | 333 | 3090 Old Todds Rd. | Lexington | KY | 541 | LEXINGTON | Michael Dee | Jesse Culbertson |  |  | STAUFFER, JACOB W. | 2021-01-04 |  | Remodel Complete | 5 | EquipmentVendor | 2023-11-07 | 2023-11-06 | 2023-11-02 | Install1 | bbw Stat3
Server Handheld | 444 | 5405 Pearl Dr. | Evansville | IN | 649 | EVANSVILLE |  | Nick Rice |  |  | JOHNSON, BRENT L. | 2022-02-25 |  | Remodel Complete | 6 | EquipmentVendor | 2023-12-07 | 2023-12-06 | 2023-12-02 | instalUser | Quote to FEE