## Sheet1
Project Type | Store Number | Address | City | State | DMA ID | DMA | RED | CM | A&E | RVP | Principal Partner | Status | Open Store | Project Status
RELOCATION | 6937 | 461 Columbia Ave | Lexington | SC | 546 | COLUMBIA SC | Michael Landru | Kevin Dalpiaz |  |  | MICHAEL IRONS | 2022-02-01 | 2023-01-15 | Under Construction
NEW | 6836 | 2812 School Street | Needville | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  | Linda Wiseley | FLENCHER, BENJAMIN | 2022-06-01 | 2023-01-18 | Under Construction
NEW | 6704 | 5227 Decker Ln | Austin | TX | 635 | AUSTIN TX | Jon Brannin | Nick Rice |  | Linda Wiseley | REEDER RATLIFF | 2022-03-09 | 2023-01-24 | Under Construction
RELOCATION | 6891 | 108 N Lincoln Dr (temp) | Troy | MO | 609 | ST. LOUIS MO | Michael Dee | Nick Rice |  |  | UMSTATTD, KEVIN | 2022-09-15 | 2023-01-24 | Under Construction
REBUILD | 4948 |  | Pflugerville | TX | 635 | AUSTIN TX |  | Nick Rice |  |  | MHR AUSTIN SONIC RESTAURANTS, LLC | 2022-10-04 | 2023-02-16 | Under Construction
NEW | 6972 | 14035 Airport Rd | GULFPORT | MS | 746 | BILOXI-GULFPORT MS | Joe Morian | Jay Bauch |  |  | NEW FRANCHISEE | 2023-02-09 | 2023-02-20 | Permits Ready
NEW | 6831 | TBD | Kahului | HI | 744 | HONOLULU HI | Joe Morian | Nick Rice |  | Bobby Jones | Prather, Edwin | 2022-03-27 | 2023-03-06 | Under Construction
NEW | 6872 | 41 IN-32 (temp) | Westfield | IN | 527 | INDIANAPOLIS IN | David Skidmore | Kevin Dalpiaz |  |  | FUGATE, TODD | 2022-04-20 | 2023-03-06 | Under Construction
NEW | 6947 | 6878 US-64 | Pottsville | AR | 693 | LITTLE ROCK-PINE BLUFF AR | Michael Dee | Kevin Dalpiaz |  |  | PORTER, DENNIS | 2022-08-08 | 2023-03-06 | Under Construction
NEW | 6895 | 12 W Market St (temp) | Stockton | CA | 862 | SACRAMENTO CA | Bonnie Gatine | Nick Rice |  |  | Singh, Surainder | 2022-08-23 | 2023-03-09 | Under Construction
NEW | 6808 | 6096 US-175 | Athens | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Judson, Matthew | 2022-06-20 | 2023-03-20 | Under Construction
NEW | 6835 | 1017 S 1150 E | Eden | ID | 757 | BOISE ID | Joe Morian | Nick Rice |  |  | Willie, Daniel L. | 2021-08-02 | 2023-03-20 | Under Construction
NEW | 6794 | 5903 Roswell Road | Sandy Springs | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | RED ARCHITECTS |  | SRI OPERATING COMPANY | 2022-09-12 | 2023-03-20 | Under Construction
NEW | 6946 | 302 S Service Rd E | Sullivan | MO | 609 | ST. LOUIS MO | Charles DeFiglio | Kevin Dalpiaz |  |  | JACOB STAUFFER | 2022-11-14 | 2023-03-20 | Under Construction
NEW | 6975 | 3004 I-30 | Greenville | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Butt, Tarik | 2022-11-07 | 2023-03-31 | Under Construction
NEW | 6762 | 524 TRIMBLE PLAZA SOUTHEAST | Leesburg | VA | 511 | WASHINGTON DC | Charles DeFiglio | Kevin Dalpiaz |  | Todd Wekenborg | BHAVESH CHANIYARA | 2022-10-03 | 2023-04-06 | Under Construction
RELOCATION | 6963 | 4601-4613 Gus Thomasson Road | Mesquite | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | BARTON, THELMA | 2022-08-17 | 2023-04-10 | Under Construction
NEW | 6951 | 13900 Landstar Blvd | Orlando | FL | 534 | ORLANDO FL | Michael Landru | Kevin Dalpiaz | Christina Hernandez |  | Quality Drive-Ins | 2023-02-02 | 2023-04-12 | In Permitting
NEW | 6902 | 8080 Bailey Rd | Pearland | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | Karedia, Karim | 2022-12-12 | 2023-04-24 | Under Construction
NEW | 6878 | TBD | Thornton | CO | 751 | DENVER CO | Joe Morian | Kevin Dalpiaz |  |  | SINGH, SURJEET | 2023-01-02 | 2023-05-13 | Under Construction
NEW | 6926 | Habersham Hills Cir. | Cornelia | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson |  |  | SRI OPERATING COMPANY | 2023-02-20 | 2023-05-25 | In Permitting
NEW | 6901 | 3301 Alliance Gateway Fwy | Fort Worth | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | CHARANJIT SINGH | 2023-02-04 | 2023-05-25 | In Permitting
NEW | 6962 | 9000 Schiro Rd (temp) | Hitchcock | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | Karedia, Karim | 2023-02-20 | 2023-05-25 | Permits Ready
NEW | 6914 |  | Jarrell | TX | 635 | AUSTIN TX | Jon Brannin | Nick Rice |  |  | MHR AUSTIN SONIC RESTAURANTS, LLC | 2023-01-02 | 2023-05-29 | Under Construction
NEW | 6807 | 5230 N Loop 1604 E | San Antonio | TX | 641 | SAN ANTONIO TX | Jon Brannin | Nick Rice |  |  | DHAROD, SUNIL | 2023-02-12 | 2023-06-03 | Permits Ready
NEW |  | 4500 San Palo Rd | Atascadero | CA | 855 | SANTA BARBARA CA | Bonnie Gatine | Nick Rice |  |  | BOPARAI, GURPREET | 2023-02-06 | 2023-06-17 | Permits Ready
NEW | 6852 | 5419 6th | Klamath Falls | OR | 813 | MEDFORD OR | Joe Morian | Nick Rice |  |  | PARROTT, STACY | 2022-11-28 | 2023-06-22 | Under Construction
NEW | 6851 | 861 Migeon Ave | Torrington | CT | 533 | HARTFORD CT | Charles DeFiglio | Kevin Dalpiaz |  |  | AHMED, MIR SABBIR | 2023-03-31 | 2023-06-30 | In Permitting
NEW | 6779 | 10712 Laurel Avenue | Santa Fe Springs | CA | 803 | LOS ANGELES CA | Joe Morian | Nick Rice |  | Bobby Jones | WESSELINK, RICHARD | 2023-03-23 | 2023-07-10 | Permits Ready
NEW | 6945 | 7007 Gulf Freeway | Houston | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  | Linda Wiseley | DHANANI, GHULAM R. | 2023-01-23 | 2023-07-11 | Permits Ready
NEW |  | 5205 27th St S | Fargo | ND | 724 | FARGO ND | David Skidmore | Kevin Dalpiaz |  |  | SAKAK, ABBAS SEYED | 2023-04-03 | 2023-07-12 | In Permitting
NEW | 6827 |  | Fernley | NV | 811 | RENO NV | Joe Morian | Kevin Dalpiaz |  | Bobby Jones | Cain, Taylor | 2023-01-24 | 2023-07-16 | In Permitting
REBUILD | 2943 |  | San Antonio | TX | 641 | SAN ANTONIO TX | Jon Brannin | Nick Rice |  |  | DHAROD, SUNIL | 2023-04-03 | 2023-07-22 | Early Stage
NEW | 6823 | TBD | Ontario | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  | Bobby Jones | WESSELINK, RICHARD | 2023-02-10 | 2023-08-05 | In Permitting
REBUILD | 3217 | 401 S. POPLAR STREET | KERMIT | TX | 633 | ODESSA TX | Jon Brannin | Rick Colon |  |  | GONZALEZ, TELESFORO | 2023-03-05 | 2023-08-09 | In Permitting
NEW | 6848 | 1800 TX-114 | Justin | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | SAHIHI, MASON | 2023-04-03 | 2023-08-11 | In Permitting
NEW |  | TBD | Bonners Ferry | ID | 881 | SPOKANE WA | Joe Morian | Kevin Dalpiaz |  |  | NEW FRANCHISEE | 2023-01-02 | 2023-08-15 | Under Construction
RELOCATION | 6909 | 281 TX-243 | Canton | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | ROGERS, DARRELL L. | 2023-04-28 | 2023-08-23 | Permits Ready
NEW | 6684 | 643 West Ventura Street | Fillmore | CA | 803 | LOS ANGELES CA | Joe Morian | Nick Rice |  | Bobby Jones | Behniwal, Rajpal Singh | 2023-01-23 | 2023-08-26 | Permits Ready
NEW |  | 1195 State Hwy NN | Ozark | MO | 619 | Springfield MO | Michael Dee | Kevin Dalpiaz |  |  | SMITH, KENNETH V. | 2023-03-27 | 2023-09-02 | Site Package App
NEW | 6877 | 601 N, FM 156 (temp) | Ponder | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ERVIN, RICHARD | 2023-02-07 | 2023-09-03 | In Permitting
RELOCATION | 6981 |  | Columbia | MO | 604 | COLUMBIA MO | Michael Dee | Nick Rice |  |  | ROGERS, DARRELL L. | 2022-11-14 | 2023-09-03 | Under Construction
NEW |  | 9701 Bluew ater Rd NW (temp) | Albuquerque | NM | 790 | ALBUQUERQUE-SANTA FE NM | Joe Morian | Nick Rice |  |  | MERRITT, KENNETH | 2023-05-21 | 2023-09-08 | Plans Started
NEW |  | 5408 Southwest Dr | Jonesboro | AR | 734 | JONESBORO AR | Michael Dee | Kevin Dalpiaz |  |  | DAVIS, RICKY P. | 2023-05-01 | 2023-09-09 | Site Package App
NEW | 6837 |  | Citrus Heights | CA | 862 | SACRAMENTO CA | Joe Morian | Nick Rice |  |  | CHARANJIV "CJ" DHALIWAL | 2023-02-06 | 2023-09-11 | Permits Ready
NEW | 6915 | 605 Paris Rd | Bogata | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | AZAM, MOHAMMED | 2022-09-02 | 2023-09-14 | Under Construction
NEW |  | 240 NW Centurion Ct (TEMP) | Lake City | FL | 561 | JACKSONVILLE FL | Michael Landru | Kevin Dalpiaz | Christina Hernandez |  | MCMILLAN, CHRISTOPHER | 2023-03-27 | 2023-09-18 | Permits Ready
NEW |  | 714 W Main St | Marion | IL | 632 | PADUCAH KY | David Skidmore | Kevin Dalpiaz |  |  | JAMES, MIKE | 2023-04-17 | 2023-09-23 | In Permitting
NEW |  | 1080 Long Run Rd, | White Oak | PA | 508 | PITTSBURGH PA | Charles DeFiglio | Kevin Dalpiaz |  |  | King, Hartley | 2023-04-22 | 2023-10-02 | In Permitting
NEW | 6950 | 20331 US 93 | Willow Beach | AZ | 753 | PHOENIX AZ | Bonnie Gatine | Nick Rice |  |  | VENTURA, OFIR | 2023-03-09 | 2023-10-05 | In Permitting
NEW |  | Collinsville, OK | Collinsville | OK | 671 | TULSA OK | Jon Brannin | Kevin Dalpiaz |  |  | SMITH, KENNETH V. | 2023-04-03 | 2023-10-10 | Site Package App
NEW | 6873 | Interquest Parkway | Colorado Springs | CO | 752 | COLORADO SPRINGS CO | Joe Morian | Jesse Culbertson | WD Partners |  | SONIC RESTAURANTS INC. | 2023-05-01 | 2023-10-16 | In Permitting
NEW | 6859 | 885 Glynn St., N | Fayetteville | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson |  |  | SRI OPERATING COMPANY | 2023-07-05 | 2023-10-25 | Site Package App
NEW |  | 682 N. Jackson St. | Houston | MS | 673 | COLUMBUS MS | Michael Dee | Kevin Dalpiaz |  |  | MCCLAIN, RONALD G. | 2023-05-10 | 2023-10-26 | Site Package App
NEW | 6898 | 13046 Flamingo Crossings Blvd (TEMP) | Winter Garden | FL | 534 | ORLANDO FL | Michael Landru | Kevin Dalpiaz |  |  | MLODINOFF, CADE | 2023-05-01 | 2023-11-01 | In Permitting
NEW | 6897 | 3298 NW 79th St (TEMP) | Gladeview | FL | 528 | MIAMI-FT. LAUDERDALE FL | Michael Landru | Kevin Dalpiaz |  |  | WENDT, ANDREW PATRICK | 2023-05-08 | 2023-11-02 | In Permitting
NEW | 6834 | 1155 Cedar Mtn Rd | Fillmore | UT | 770 | SALT LAKE CITY UT | Joe Morian | Jay Bauch |  |  | Verma, Vishi | 2023-01-12 | 2023-11-03 | Permits Ready
NEW |  | Palmview, TX | Palmview | TX | 636 | HARLINGEN TX | Jon Brannin | Nick Rice |  |  | TREVINO, ALFREDO | 2023-07-16 | 2023-11-03 | Site Package App
RELOCATION | 6864 | 6614 Youree Drive | Shreveport | LA | 612 | SHREVEPORT LA | Jon Brannin | Nick Rice |  |  | ROGERS, DARRELL L. | 2023-08-09 | 2023-11-05 | Site Package App
NEW |  | Bonds Ranch Rd | Fort Worth | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | CHRIS ROACH (SONIC) | 2023-07-20 | 2023-11-07 | Site Package App
NEW |  | E. First Street | Prosper | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | PROSPER INDEPENDENT SCHOOL DISTRICT | 2023-07-21 | 2023-11-08 | Site Package App
NEW |  | I-20 & State Park Hwy | Tyler | TX | 709 | TYLER TX | Jon Brannin | Nick Rice |  |  | Butt, Tarik | 2023-07-21 | 2023-11-08 | Site Package App
NEW | 6892 | 2510 W Parrish Ave | Owensboro | KY | 649 | EVANSVILLE IN | David Skidmore | Kevin Dalpiaz |  |  | GUTHRIE, PENNY | 2023-06-02 | 2023-11-09 | Plans Started
NEW |  | 777 Cranston St. | Cranston | RI | 521 | PROVIDENCE RI | Charles DeFiglio | Kevin Dalpiaz |  |  | STACK, CHRISTOPHER D. | 2023-03-12 | 2023-11-10 | In Permitting
NEW | 6903 | 1006 Stelton Rd | Piscataway | NJ | 501 | NEW YORK NY | Charles DeFiglio | Kevin Dalpiaz |  |  | Shah, Sachin | 2023-06-05 | 2023-11-12 | Plans Started
NEW | 6957 | Hometown Ave (TEMP) | Blairsville | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | Christina Hernandez |  | SRI OPERATING COMPANY | 2023-07-26 | 2023-11-13 | Site Package App
NEW | 6841 | TBD new construction | Lincoln | NE | 722 | LINCOLN NE | Michael Dee | Kevin Dalpiaz |  |  | ESCH, INC. | 2023-06-05 | 2023-11-18 | In Permitting
NEW | 6817 | TBD, new construction | Memphis | TN | 640 | MEMPHIS TN | Michael Dee | Kevin Dalpiaz |  |  | SOLBERG, RONALD A. | 2023-06-01 | 2023-11-18 | Plans Started
NEW |  | I-10 (Seguin, TX) | Seguin | TX | 641 | SAN ANTONIO TX | Jon Brannin | Nick Rice | Christina Hernandez |  | Butt, Tarik | 2023-06-30 | 2023-11-23 | In Permitting
NEW |  | 4610 Central Way | Fairfield | CA | 862 | SACRAMENTO CA | Bonnie Gatine | Nick Rice |  |  | DHALIWAL, CHARANJIV | 2023-08-14 | 2023-12-02 | Site Package App
NEW | 6949 | 310 N Main Ave | Goldsby | OK | 650 | OKLAHOMA CITY OK | Jon Brannin | Kevin Dalpiaz |  |  | MOORE, JOE | 2023-06-28 | 2023-12-05 | Plans Started
NEW |  | 719 W Ocean Blvd | Los Fresnos | TX | 636 | HARLINGEN TX | Jon Brannin | Nick Rice |  |  | REEDER RATLIFF | 2023-08-19 | 2023-12-07 | Site Package App
NEW | 6941 | 214 S Salem St | Randolph | NJ | 501 | NEW YORK NY | Charles DeFiglio | Kevin Dalpiaz |  |  | NEW FRANCHISEE | 2023-07-12 | 2023-12-15 | Plans Started
NEW | 6832 | 204 Farm to Market Road 2641 | Lubbock | TX | 651 | LUBBOCK TX | Jon Brannin | Nick Rice |  | Bobby Jones | RODNEY WARREN | 2023-08-07 | 2023-12-19 | Permits Ready
NEW | 6846 | 115 Redwater Boulevard West | Redwater | TX | 612 | SHREVEPORT LA | Jon Brannin | Nick Rice |  | Todd Wekenborg | MCQUILLIAMS, ALVIN | 2023-06-19 | 2023-12-20 | Site Package App
NEW | 6754 | 6688 FM 741 | Forney | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | ALAQRABAWY, MOHAMMAD | 2023-02-06 | 2023-12-21 | Permits Ready
NEW | 6811 | 1084 West Highway 79 | Franklin | TX | 625 | WACO TX | Jon Brannin | Nick Rice |  | Linda Wiseley | FLENCHER, BENJAMIN | 2023-08-14 | 2023-12-21 | In Permitting
NEW |  | 402 S Memorial St. | Riesel | TX | 625 | WACO TX | Jon Brannin | Nick Rice |  |  | AZAM, MOHAMMED | 2023-06-20 | 2023-12-21 | Plans Started
NEW |  | 87125 I-20 W | Santo | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Mohamed Sharaf | 2023-04-30 | 2023-12-21 | Plans Started
NEW |  | 2200 W Lake Bardwell Dr | Ennis | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Mohamed Sharaf | 2023-05-30 | 2023-12-28 | Plans Started
NEW |  | Hwy 77 (N Alamo St) | Refugio | TX | 600 | CORPUS CHRISTI TX | Jon Brannin | Nick Rice |  |  | PUNJWANI, TAJUDDIN | 2023-09-09 | 2023-12-28 | Site Package App
NEW |  | 730 Broadway | Brooklyn | NY | 501 | NEW YORK NY | Charles DeFiglio | Kevin Dalpiaz |  |  | NEW FRANCHISEE | 2023-09-03 | 2024-01-11 | Site Package App
NEW |  |  | Cave Springs | AR | 670 | FT. SMITH AR | Michael Dee | Kevin Dalpiaz |  |  | ESCH, INC. | 2023-09-27 | 2024-01-15 | Site Package Prep
NEW |  |  | Hohenwald | TN | 659 | NASHVILLE TN | Michael Dee | Kevin Dalpiaz |  |  | JOHNSON, BRENT L. | 2023-09-27 | 2024-01-15 | Site Package Prep
NEW |  | 52 Fulton St. | New York | NY | 501 | NEW YORK NY | Charles DeFiglio | Kevin Dalpiaz |  |  | SUTAR, SHIRAZ | 2023-09-05 | 2024-01-15 | Site Package App
NEW |  |  | San Bernardino | CA | 803 | LOS ANGELES CA |  | Jay Bauch |  |  | NEW FRANCHISEE | 2023-07-14 | 2024-01-15 | Site Package App
NEW |  |  | Anna | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | WARREN, RODNEY W. | 2023-09-29 | 2024-01-17 | LOI
RELOCATION | 1616 | 1817 Avenue F | Bay City | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | GARZA, JOEL | 2023-09-29 | 2024-01-17 | LOI
RELOCATION |  | 521 N Main St | Miami | OK | 603 | JOPLIN MO | Jon Brannin | Kevin Dalpiaz |  |  | SMITH, LARRY | 2023-09-29 | 2024-01-17 | LOI
RELOCATION | 5262 | 3502 Houston Hwy | Victoria | TX | 626 | VICTORIA TX | Jon Brannin | Nick Rice |  |  | SANDHOP JR., GARLAND | 2023-09-29 | 2024-01-17 | LOI
NEW |  |  | San Antonio | TX | 641 | SAN ANTONIO TX | Jon Brannin | Nick Rice |  |  | BARNETT JR., DALLAS CODY | 2023-10-09 | 2024-01-27 | LOI
NEW |  | 3037 PIEDMONT RD NE | Atlanta | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | Christina Hernandez |  | SRI OPERATING COMPANY | 2023-10-10 | 2024-01-28 | LOI
NEW |  | 3000 IN-135 (Temp) | Greenwood | IN | 527 | INDIANAPOLIS IN | David Skidmore | Kevin Dalpiaz |  |  | FUGATE, TODD | 2023-08-21 | 2024-01-28 | Site Package App
NEW |  | 12451 Old US 95 | Henderson | NV | 839 | LAS VEGAS NV |  | Jay Bauch |  |  | NEW FRANCHISEE | 2023-07-21 | 2024-01-28 | Site Package App
NEW |  | NW 2nd Street | Kerens | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ISKANDARANI, HOUSSAM | 2023-10-10 | 2024-01-28 | Site Package Prep
NEW | 6783 | 6421 SW Archer | Gainesville | FL | 592 | GAINESVILLE FL | Jon Brannin | Kevin Dalpiaz |  | Todd Wekenborg | R. TRENT WATKINS | 2023-08-07 | 2024-01-29 | In Permitting
NEW |  | TBD | Oak Harbor | WA | 819 | SEATTLE WA | Bonnie Gatine | Kevin Dalpiaz |  |  | PATEL, JASMIN R. | 2023-07-24 | 2024-01-29 | Plans Started
NEW |  |  | Ceres | CA | 862 | SACRAMENTO CA | Bonnie Gatine | Nick Rice |  |  | Dhanda, Benny | 2023-09-18 | 2024-02-05 | Site Package App
NEW |  | 16750 Dumfries Rd | Dumfries | VA | 511 | WASHINGTON DC | Charles DeFiglio | Kevin Dalpiaz |  |  | COVEY, STEVE | 2023-08-23 | 2024-02-05 | Site Package App
NEW |  |  | Fayetteville | AR | 670 | FT. SMITH AR | Michael Dee | Kevin Dalpiaz |  |  | SMITH, KENNETH V. | 2023-10-21 | 2024-02-08 | LOI
NEW | 6867 | Panther Creek Pkwy | Frisco | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Mohamed Sharaf | 2023-06-22 | 2024-02-11 | Site Package App
RELOCATION | 2953 |  | Stilwell | OK | 671 | TULSA OK | Jon Brannin | Kevin Dalpiaz |  |  | SMITH, KENNETH V. | 2023-10-26 | 2024-02-13 | LOI
NEW |  |  | Baker | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  |  | LEE, DENISE | 2023-10-29 | 2024-02-16 | Site ID
NEW |  |  | Kaneohe | HI | 744 | HONOLULU HI | Joe Morian | Nick Rice |  |  | EDWIN PRATHER | 2023-10-29 | 2024-02-16 | Site ID
NEW |  |  | Lake Elsinore | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  |  | WESSELINK, RICHARD | 2023-10-29 | 2024-02-16 | Site ID
NEW |  |  | Perris | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  |  | WESSELINK, RICHARD | 2023-10-29 | 2024-02-16 | Site ID
NEW |  |  | Valencia | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  |  | WESSELINK, RICHARD | 2023-10-29 | 2024-02-16 | Site ID
NEW | 6853 | 733 Kent Pratt Blvd | Longmont | CO | 751 | DENVER CO | Joe Morian | Kevin Dalpiaz |  |  | SURJEET SINGH | 2023-09-10 | 2024-02-17 | Plans Started
NEW |  | 11165 W 63rd Pl (temp) | Arvada | CO | 751 | DENVER CO | Joe Morian | Kevin Dalpiaz |  |  | SINGH, SURJEET | 2023-09-15 | 2024-03-01 | Plans Started
NEW |  |  | Alleyton | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | Randhawa, Jaswinder | 2023-11-16 | 2024-03-05 | LOI
NEW |  | TBD, new construction | Elkhorn | NE | 652 | OMAHA NE | Michael Dee | Kevin Dalpiaz |  |  | MORRISON, BRYANT D. | 2023-09-11 | 2024-03-08 | In Permitting
NEW |  | W Cook Street | Josephine | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ALAQRABAWY, MOHAMMAD | 2023-11-21 | 2024-03-10 | Site Package App
NEW |  |  | Lone Tree | CO | 751 | DENVER CO | Joe Morian | Kevin Dalpiaz |  |  | SINGH, SURJEET | 2023-10-18 | 2024-03-11 | LOI
NEW |  | 900 N Vermillion St (temp) | Danville | IL | 648 | CHAMPAIGN IL | David Skidmore | Kevin Dalpiaz |  |  | Patrick Wampler | 2023-08-29 | 2024-03-12 | Site Package App
NEW | 6908 | 4031 Hwy 280 | Alexander City | AL | 698 | MONTGOMERY AL | Michael Dee | Kevin Dalpiaz |  |  | JOHNOTHAN BLY GRAVLEE | 2023-09-17 | 2024-03-17 | In Permitting
NEW | TBD | 897 Craft Road | Olive Branch | MS | 640 | MEMPHIS TN | Michael Dee | Kevin Dalpiaz |  | Todd Wekenborg | RONALD SOLBERG | 2023-11-30 | 2024-03-19 | Site ID
NEW |  | TBD, new construction | Piperton | TN | 640 | MEMPHIS TN | Michael Dee | Kevin Dalpiaz |  |  | RONALD SOLBERG | 2023-11-30 | 2024-03-19 | Site ID
NEW | 6958 | 11235 Tara Blvd | Lovejoy | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | Christina Hernandez |  | SRI OPERATING COMPANY | 2023-12-03 | 2024-03-22 | Site Package App
RELOCATION |  | 1805 Antonio St | Antonio | TX | 765 | EL PASO TX | Joe Morian | Nick Rice |  |  | BOBBY MERRITT ESTATE | 2023-12-08 | 2024-03-27 | Early Stage
REBUILD | 1560 | 7708 Burnet Rd | Austin | TX | 635 | AUSTIN TX | Jon Brannin |  |  |  | REEDER RATLIFF | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  | 1995 Military Rd | Buffalo | NY | 514 | BUFFALO NY | Charles DeFiglio | Kevin Dalpiaz |  |  | DIPIRRO, KEVIN | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  | 4480 E Covell Rd | Edmond | OK | 650 | OKLAHOMA CITY OK | Jon Brannin | Kevin Dalpiaz |  | Linda Wiseley | WINTERS, CHRIS | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  |  | Magnolia | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | BARNETT JR., DALLAS CODY | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  | 999 | St. George | UT | 770 | SALT LAKE CITY UT | Joe Morian | Kevin Dalpiaz |  |  | Kelleher, Timothy | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  | 11214 E Main St | Tomball | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  | Linda Wiseley | BARNETT JR., DALLAS CODY | 2023-12-08 | 2024-03-27 | Early Stage
RELOCATION | 3466 | 1003 N Hwy 377 | Whitesboro | TX | 657 | SHERMAN-ADA TX-OK | Jon Brannin | Nick Rice |  |  | ROGERS, DARRELL L. | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  | 3516 Maple Ave | Zanesville | OH | 596 | ZANESVILLE OH | Charles DeFiglio |  |  |  | JACOB STAUFFER | 2023-12-08 | 2024-03-27 | Early Stage
NEW |  | 14022-14036 Horizon Boulevard | Horizon City | TX | 765 | EL PASO TX | Jon Brannin | Nick Rice |  | Bobby Jones | MERRITT, BOBBY | 2024-01-21 | 2024-03-30 | LOI
NEW | 6810 | 1870 W Victory Way | Craig | CO | 751 | DENVER CO | Joe Morian | Kevin Dalpiaz |  |  | SIGLER, P. DEAN | 2023-07-24 | 2024-04-01 | Permits Ready
NEW |  | 12971 Camino Real | Kyle | TX | 635 | AUSTIN TX | Jon Brannin | Nick Rice |  |  | Karedia, Karim | 2023-12-13 | 2024-04-01 | Site Package Prep
NEW |  | S. Alton Blvd | Alton | TX | 636 | HARLINGEN TX | Jon Brannin | Nick Rice |  |  | TREVINO, ALFREDO | 2023-12-14 | 2024-04-02 | Site Package App
RELOCATION | 1618 | 144 W 4th Ave | Bristow | OK | 671 | TULSA OK | Jon Brannin | Kevin Dalpiaz |  | Bobby Jones | BARNES, ROBERT C. | 2023-10-26 | 2024-04-03 | Site Package App
NEW |  | Parker Road | Lewisville | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | CHRIS ROACH (SONIC) | 2023-12-16 | 2024-04-04 | Site Package App
NEW |  | Hwy 71 | Smithville | TX | 635 | AUSTIN TX | Jon Brannin | Nick Rice |  |  | REEDER RATLIFF | 2023-08-20 | 2024-04-05 | Site Package Prep
NEW |  | 1051 FM 2181 | Corinth | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | CHRIS ROACH (SONIC) | 2023-12-24 | 2024-04-12 | Site Package App
NEW |  | 795 W 5th St (temp) | San Bernardino | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  |  | WESSELINK, RICHARD | 2023-12-05 | 2024-04-13 | Plans Started
NEW |  | Sonoma Ranch Blvd | Las Cruces | NM | 765 | EL PASO TX | Joe Morian | Nick Rice |  | Bobby Jones | MERRITT, BOBBY | 2034-08-30 | 2024-04-18 | Site Package Prep
NEW | 6894 | 8009 Telegraph Rd (temp) | Taylor | MI | 505 | DETROIT MI | David Skidmore | Kevin Dalpiaz |  |  | SOAR Restaurants, LLC | 2023-11-22 | 2024-05-06 | Site Package App
NEW |  |  | Warenton | MO | 609 | ST. LOUIS MO | Michael Dee | Kevin Dalpiaz |  |  | KEVIN UMSTATTD | 2023-10-29 | 2024-05-06 | Site ID
NEW |  | TBD, new construction | Headland | AL | 606 | DOTHAN AL | Michael Dee | Kevin Dalpiaz |  |  | MCMILLAN, CHRISTOPHER | 2023-11-03 | 2024-05-09 | Site Package App
NEW | 6906 | 1115 S. Airport Way | Manteca | CA | 862 | SACRAMENTO CA | Bonnie Gatine | Nick Rice |  |  | Singh, Surainder | 2024-01-25 | 2024-05-14 | Plans Started
NEW |  | 1105 Fall River Ave | Seekonk | MA | 521 | PROVIDENCE RI | Charles DeFiglio | Kevin Dalpiaz |  |  | STACK, CHRISTOPHER D. | 2023-10-06 | 2024-05-16 | Site Package App
NEW |  |  | Scott | LA | 642 | LAFAYETTE LA | Jon Brannin | Kevin Dalpiaz |  |  | JAMES, MIKE | 2023-12-13 | 2024-05-21 | LOI
NEW |  |  | New Waverly | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | FLENCHER, BENJAMIN | 2024-02-02 | 2024-05-22 | Site ID
NEW |  |  | Rhome | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ERVIN, RICHARD | 2024-02-02 | 2024-05-24 | Site Package App
NEW |  |  | Ferris | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ALAQRABAWY, MOHAMMAD | 2024-02-05 | 2024-05-25 | Site ID
NEW | 6967 | Floyd | Austell | GA | 524 | ATLANTA GA | Michael Landru | Kevin Dalpiaz | Christina Hernandez |  | ATTICUS FRANCHISE GROUP | 2023-12-18 | 2024-05-26 | Site Package App
NEW |  | TBD | Cayce | SC | 546 | COLUMBIA SC | Michael Landru | Kevin Dalpiaz | Christina Hernandez |  | IRONS, MICHAEL | 2023-12-08 | 2024-05-26 | Site Package Prep
NEW |  | Rosharon, TX | Rosharon | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | Karedia, Karim | 2023-05-09 | 2024-05-30 | In Permitting
NEW | 6862 | 466 W Klein Rd | New Braunfels | TX | 641 | SAN ANTONIO TX | Jon Brannin | Nick Rice |  |  | BARNETT JR., DALLAS CODY | 2024-02-12 | 2024-06-01 | Plans Started
NEW | 6842 | 3201 US-27 (TEMP) | Clermont | FL | 534 | ORLANDO FL | Michael Landru | Kevin Dalpiaz |  |  | R. TRENT WATKINS | 2023-12-31 | 2024-06-05 | Permits Ready
NEW |  |  | Foster | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | RYAN FLENCHER | 2024-02-25 | 2024-06-14 | Early Stage
RELOCATION | 6910 |  | El Campo | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  |  | MERSIOSKY, MICHAEL E. | 2023-12-19 | 2024-06-24 | Site Package App
NEW |  |  | Covington | LA | 622 | NEW ORLEANS LA | Jon Brannin | Kevin Dalpiaz |  |  | PRAY, GABE | 2024-03-17 | 2024-07-05 | LOI
NEW |  | 17639 Bellflower Blvd | Bellflower | CA | 803 | LOS ANGELES CA | Bonnie Gatine | Nick Rice |  |  | WESSELINK, RICHARD | 2024-03-11 | 2024-07-12 | Site Package App
NEW | 6922 |  | Midland | TX | 633 | ODESSA TX | Jon Brannin | Nick Rice |  |  | REEDER RATLIFF | 2024-03-26 | 2024-07-14 | Site Package App
NEW |  | 6000 Marine Creek Pkwy | Fort Worth | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ERVIN, RICHARD | 2024-03-12 | 2024-07-22 | Site Package App
NEW |  | TBD | Stockton | CA | 862 | SACRAMENTO CA | Joe Morian | Nick Rice |  |  | CHARANJIV DHALIWAL | 2023-11-09 | 2024-08-05 | In Permitting
NEW | 6918 |  | Hugoton | KS | 678 | Wichita-Hutchinson KS | Michael Dee | Kevin Dalpiaz |  |  | VAN DORN, DWIGHT | 2024-03-01 | 2024-08-12 | Site Package App
NEW |  | 1155 Burlington Dr | Bismarck | ND | 687 | MINOT ND | David Skidmore | Kevin Dalpiaz |  |  | SAKAK, ABBAS SEYED | 2024-03-18 | 2024-08-15 | LOI
NEW |  | 2075 W Spring St (TEMP) | Monroe | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | Christina Hernandez |  | SRI OPERATING COMPANY | 2024-05-17 | 2024-09-04 | LOI
NEW |  | TBD McCarran | Reno | NV | 811 | RENO NV | Bonnie Gatine | Kevin Dalpiaz |  |  | Cain, Taylor | 2024-05-25 | 2024-09-12 | LOI
NEW | 6861 | 309 Fields Town Rd | Gardendale | AL | 630 | BIRMINGHAM AL | Michael Dee | Kevin Dalpiaz |  |  | JAMES P BATCHELLER | 2024-03-11 | 2024-10-07 | Site Package App
NEW | TBD | TBD | Kapolei | HI | 744 | HONOLULU HI | Joe Morian | Nick Rice |  | Bobby Jones | Prather, Edwin | 2023-08-03 | 2024-10-20 | Site Package Prep
NEW | 6959 | 286 S Main St | Cleveland | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | Christina Hernandez |  | SRI OPERATING COMPANY | 2024-07-08 | 2024-10-26 | Site Package App
NEW |  | 1551 W Main St | Salem | IL | 609 | ST. LOUIS MO | David Skidmore | Kevin Dalpiaz |  |  | JAMES, MIKE | 2024-07-09 | 2024-10-27 | Site Package App
NEW |  | Pinyon Road | Broken Bow | OK | 612 | SHREVEPORT LA | Jon Brannin | Kevin Dalpiaz |  | Todd Wekenborg | ALVIN MCQUILLIAMS | 2023-10-31 | 2024-10-30 | Site ID
NEW |  | TBD 163rd | Surprise | AZ | 753 | PHOENIX AZ | Bonnie Gatine | Nick Rice |  |  | REEDER RATLIFF | 2024-07-12 | 2024-10-30 | Site Package App
NEW |  | 3271 Liberty Rd | Galt | CA | 862 | SACRAMENTO CA | Bonnie Gatine | Nick Rice |  |  | Dhanda, Benny | 2024-08-06 | 2024-11-03 | Site Package App
RELOCATION |  | 410 US Highway 380 | Bridgeport | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | ROGERS, DARRELL L. | 2024-08-28 | 2024-11-06 | Site ID
NEW |  |  | Waxahachie | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Mohamed Sharaf | 2024-07-24 | 2024-11-11 | Early Stage
NEW |  | 3002 N Water St | Decatur | IL | 648 | CHAMPAIGN IL | David Skidmore | Kevin Dalpiaz |  |  | JAMES, MIKE | 2024-08-01 | 2024-11-19 | LOI
NEW |  |  | Honolulu | HI | 744 | HONOLULU HI | Joe Morian | Nick Rice |  |  | EDWIN PRATHER | 2024-08-02 | 2024-11-20 | Early Stage
NEW |  |  | Battle Ground | WA | 820 | PORTLAND OR | Bonnie Gatine | Kevin Dalpiaz |  |  | WETSEL, JESS | 2024-08-05 | 2024-11-23 | Site ID
NEW |  | 36 State Highway 24 | Cooper | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | ALAQRABAWY, MOHAMMAD | 2023-12-08 | 2024-11-23 | Early Stage
NEW |  | 2930 Pleasant Valley Rd | Sachse | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | ALAQRABAWY, MOHAMMAD | 2024-08-18 | 2024-12-06 | Site Package App
NEW | 6825 | 8963 Texas 211 | San Antonio | TX | 641 | SAN ANTONIO TX | Jon Brannin | Nick Rice |  | Linda Wiseley | BARNETT JR., DALLAS CODY | 2023-05-25 | 2024-12-09 | Site Package App
RELOCATION |  |  | Abilene | TX | 662 | ABILENE-SWEETWATER TX | Jon Brannin | Nick Rice |  |  | ROGERS, DARRELL L. | 2024-08-26 | 2024-12-14 | Early Stage
NEW |  |  | Ashland | MO | 604 | COLUMBIA MO | Michael Dee | Kevin Dalpiaz |  |  | BALL, ROBERT | 2024-08-31 | 2024-12-19 | Early Stage
NEW |  | 1897 S Main Street | Waynesville | NC | 545 | GREENVILLE NC | Michael Landru | Kevin Dalpiaz |  |  | A.R. GUS MORRIS | 2024-09-28 | 2025-01-16 | Site Package Prep
NEW |  |  | Prosper | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | REEDER RATLIFF | 2024-10-06 | 2025-01-24 | LOI
NEW |  |  | Bonner Springs | KS | 616 | KANSAS CITY MO | Michael Dee | Kevin Dalpiaz |  |  | SERJ DRIVE-IN KANSAS, LLC | 2024-10-08 | 2025-01-26 | Site ID
NEW |  |  | Shreveport | LA | 612 | SHREVEPORT LA | Jon Brannin | Nick Rice |  |  | ROGERS, DARRELL L. | 2024-10-26 | 2025-02-13 | Early Stage
RELOCATION |  | 202 Harper Avenue Northwest | Lenoir | NC | 517 | CHARLOTTE NC | Charles DeFiglio | Kevin Dalpiaz |  | Todd Wekenborg | ROGERS, DARRELL L. | 2024-12-06 | 2025-03-26 | Early Stage
RELOCATION |  | 1529 N Morley St | Moberly | MO | 604 | COLUMBIA MO | Michael Dee | Nick Rice |  | Bobby Jones | ROGERS, DARRELL L. | 2024-11-25 | 2025-04-15 | Site Package Prep
NEW | 6685 | 8207 6TH STREET | Wellington | CO | 751 | DENVER CO | Joe Morian | Kevin Dalpiaz |  | Bobby Jones | WILLIAM DAVID BEARD, JR. | 2023-09-06 | 2025-04-23 | Site Package Prep
NEW |  |  | Lecanto | FL | 539 | TAMPA FL | Michael Landru | Kevin Dalpiaz | Christina Hernandez |  | MCMILLAN, CHRISTOPHER | 2024-12-20 | 2025-05-29 | Site Package Prep
NEW |  | TBD | Evans | GA | 520 | AUGUSTA GA | Michael Landru | Kevin Dalpiaz |  |  | RATLIFF, REEDER E. | 2025-03-02 | 2025-06-27 | Site ID
NEW |  |  | Lincoln | NE | 722 | LINCOLN NE | Michael Dee | Kevin Dalpiaz |  |  | ANTHONY SHERMAN | 2025-08-23 | 2025-12-11 | Early Stage
NEW |  | 601 US-84 | Cairo | GA | 530 | TALLAHASSEE FL | Michael Landru | Kevin Dalpiaz | Christina Hernandez |  | MCMILLAN, CHRISTOPHER | 2025-08-30 | 2025-12-18 | Site Package Prep
NEW |  | 6008 Farm to Market 307 | Midland | TX | 633 | ODESSA TX | Jon Brannin | Nick Rice |  | Bobby Jones | REEDER RATLIFF | 2025-08-30 | 2025-12-18 | Site ID
NEW |  | 21 Sparta Road | North Wilkesboro | NC | 518 | GREENSBORO NC | Michael Landru | Kevin Dalpiaz |  | Todd Wekenborg | J. DUDLEY PARKER | 2025-10-28 | 2026-02-15 | Early Stage
NEW |  | 2105 S Waukesha St (TEMP) | Bonifay | FL | 656 | PANAMA CITY FL | Michael Landru | Kevin Dalpiaz |  |  | MCMILLAN, CHRISTOPHER | 2025-10-04 | 2026-04-07 | Site Package App
NEW |  | 503 Laurence Drive | Heath | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | ALAQRABAWY, MOHAMMAD | 2026-06-19 | 2026-08-28 | Site ID
RELOCATION |  | State Highway Y | Belton | MO | 616 | KANSAS CITY MO | Michael Dee | Nick Rice |  | Bobby Jones | ROGERS, DARRELL L. | 2023-09-06 | 2026-11-13 | Early Stage
REBUILD | 1028 | 208 S WALTON BLVD | BENTONVILLE | AR | 670 | FT. SMITH AR | Michael Dee | Julieann Chism | Christina Hernandez |  | ESCH, INC. | 2023-05-28 |  | Plans Started
REBUILD | 1113 | 306 E Main St | Huntsville | AR | 670 | FT. SMITH AR | Michael Dee | Jesse Culbertson |  |  | STAUFFER, JACOB W. | 2021-01-04 |  | Remodel Complete
REBUILD | 1223 | 1108 W. JACKSON | OZARK | MO | 619 | Springfield MO |  | Nick Rice |  |  | JOHNSON, BRENT L. | 2022-02-25 |  | Remodel Complete
REBUILD | 1945 | 1120 W. SUNSET DRIVE | EL RENO | OK | 650 | OKLAHOMA CITY OK | Jon Brannin | Nick Rice | Christina Hernandez |  | WINTERRINGER, BRIAN | 2022-08-19 |  | Under Construction
REBUILD | 2189 | 301 EAST MAIN STREET | HEALDTON | OK | 657 | SHERMAN-ADA TX-OK |  | Julieann Chism |  |  | MOORE, JOE | 2021-11-01 |  | Remodel Complete
REBUILD | 3503 | 2219 MADISON STREET | CLARKSVILLE | TN | 659 | NASHVILLE TN | Michael Dee |  |  |  | STANFILL, JERRY | 2023-05-23 |  | Potential