## Sheet1
Project Type | Store Number | Address | City | State | DMA ID | DMA | RED | CM | A&E | RVP | Principal Partner | Status | Open Store | Project Status | Order Status Board Vendor | Order Status Board Status | OSB | Ship Date | Shipping Carrier | Tracking Number | Delivery Date | Installation Vendor | Install Status | Install Date | Install Time | Install Tech Number | Manager Name | Manager Number | Manager Checkout | Photo Deliverables | Lead Tech | Install End | Signoffs | Test Transactions | Install Project Status | Revisit Date | Cost | Install Notes | Install Type
Order Status Board | 6937 | 461 Columbia Ave | Lexington | SC | 546 | COLUMBIA SC | Michael Landru | Kevin Dalpiaz |  |  | MICHAEL IRONS | 2022-02-01 | 2023-01-15 | Under Construction | Comcast | Pending delivery date | 7 | 2023-01-15 | 8989 | 1234 | 2023-12-15 | NCR | Contact Complete [31/Aug] | 2023-12-25 | Daytime | 33 | SAN | 3456669 | Not completed | Not Received | Stan | 2023-12-30 | Not Submitted | Yes | Issues | 2024-02-02 | 88888 | Re-Imaging | Network Upgrade
Order Status Board | 6836 | 2812 School Street | Needville | TX | 618 | HOUSTON TX | Jon Brannin | Nick Rice |  | Linda Wiseley | FLENCHER, BENJAMIN | 2022-06-01 | 2023-01-18 | Under Construction | Comcast | Order Pending FEE Approval | 9 | 2023-12-18 | 8989 | 5678 | 2024-01-18 | NCR | Contact Complete [11/Aug] | 2024-01-28 | Daytime | 34 | GAN | 3456680 | Pending document | Complete | Terrance Gaines | 2024-02-02 | Submitted | No | Active | 2024-03-07 | 99999 | Memory | Network Upgrade
Order Status Board | 6704 | 5227 Decker Ln | Austin | TX | 635 | AUSTIN TX | Jon Brannin | Nick Rice |  | Linda Wiseley | REEDER RATLIFF | 2022-03-09 | 2023-01-24 | Under Construction | Comcast | Scheduled | 5 | 2024-11-19 | 8989 | 9101 | 2024-02-21 | NCR | Not Required | 2024-03-02 | Daytime | 35 | MAN | 3456691 | Complete | Photos Missing | Stan | 2024-03-07 | Not Submitted | No | Active | 2024-04-10 | 111110 | Re-Imaging | Network Upgrade
Order Status Board | 6891 | 108 N Lincoln Dr (temp) | Troy | MO | 609 | ST. LOUIS MO | Michael Dee | Nick Rice |  |  | UMSTATTD, KEVIN | 2022-09-15 | 2023-01-24 | Under Construction | Comcast | Shipped | 3 | 2025-10-22 | 8989 | 1112 | 2024-03-26 | NCR | Contact Complete [31/Oct] | 2024-04-05 | Overnight | 36 | PAN | 3456702 | Complete with Issues | Not Received | Anderson | 2024-04-10 | Copy Requested | Yes | Active | 2024-05-14 | 122221 | Memory | Network Upgrade
Order Status Board | 6972 | 14035 Airport Rd | GULFPORT | MS | 746 | BILOXI-GULFPORT MS | Joe Morian | Jay Bauch |  |  | NEW FRANCHISEE | 2022-10-04 | 2023-02-16 | Permits Ready | Comcast | Order Approved | 2 | 2026-09-24 | 8989 | 1314 | 2024-04-29 | NCR | Not Required | 2024-05-09 | Overnight | 37 | RAN | 3456713 | Not completed | Complete | Ellsworth Sheldon | 2024-05-14 | Submitted | Yes | Active | 2024-06-17 | 133332 | Re-Imaging | Network Upgrade
Order Status Board | 6831 | TBD | Kahului | HI | 744 | HONOLULU HI | Joe Morian | Nick Rice |  | Bobby Jones | Prather, Edwin | 2023-02-09 | 2023-02-20 | Under Construction | Comcast | Shipped | 1 | 2027-08-27 | 8989 | 1516 | 2024-06-02 | NCR | Contact Complete [31/Nov] | 2024-06-12 | Overnight | 38 | HAN | 3456724 | Pending document | Photos Missing | Terrance Gaines | 2024-06-17 | Not Submitted | Yes | Active | 2024-07-21 | 144443 | Memory | Network Upgrade
Order Status Board | 6872 | 41 IN-32 (temp) | Westfield | IN | 527 | INDIANAPOLIS IN | David Skidmore | Kevin Dalpiaz |  |  | FUGATE, TODD | 2022-03-27 | 2023-03-06 | Under Construction | Comcast | Order Approved | 6 | 2028-07-29 | 8989 | 1718 | 2024-07-06 | NCR | Not Required | 2024-07-16 | Overnight | 39 | KAN | 3456735 | Complete | Photos Missing | Ellsworth Sheldon | 2024-07-21 | Submitted | N/A | Issues | 2024-08-24 | 155554 | Re-Imaging | Network Upgrade