## Sheet1
Project Type | Store Number | Address | City | State | DMA ID | DMA | RED | CM | A&E | RVP | Principal Partner | Status | Open Store | Project Status | Order Accuracy Vendor | Order Accuracy Status | Bakery Printer | Dual Cup Label | DT Expo | FC Expo | Ship Date | Shipping Carrier | Tracking Number | Delivery Date | Installation Vendor | Install Status | Install Date | Install Time | Install Tech Number | Manager Name | Manager Number | Manager Checkout | Photo Deliverables | Lead Tech | Install End | Signoffs | Test Transactions | Install Project Status | Revisit Date | Cost | Install Notes | Install Type
Order Accuracy | 6947 | 6878 US-64 | Pottsville | AR | 693 | LITTLE ROCK-PINE BLUFF AR | Michael Dee | Kevin Dalpiaz |  |  | PORTER, DENNIS | 2022-02-01 | 2023-01-15 | Under Construction | Comcast | Pending delivery date | 5 | 7 | 9 | 10 | 2023-01-15 | 5667 | 6543 | 2023-12-15 | NCR | Contact Complete [31/Aug] | 2023-12-25 | Daytime | 33 | SAN | 3456669 | Not completed | Not Received | Stan | 2023-12-30 | Not Submitted | Yes | Issues | 2024-02-02 | 88888 | Re-Imaging | Network Upgrade
Order Accuracy | 6895 | 12 W Market St (temp) | Stockton | CA | 862 | SACRAMENTO CA | Bonnie Gatine | Nick Rice |  |  | Singh, Surainder | 2022-06-01 | 2023-01-18 | Under Construction | Comcast | Order Pending FEE Approval | 6 | 9 | 11 | 12 | 2023-12-18 | 6754 | 7654 | 2024-01-18 | NCR | Contact Complete [11/Aug] | 2024-01-28 | Daytime | 34 | GAN | 3456680 | Pending document | Complete | Terrance Gaines | 2024-02-02 | Submitted | No | Active | 2024-03-07 | 99999 | Memory | Network Upgrade
Order Accuracy | 6808 | 6096 US-175 | Athens | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Judson, Matthew | 2022-03-09 | 2023-01-24 | Under Construction | Comcast | Scheduled | 7 | 11 | 13 | 14 | 2024-11-19 | 7841 | 8765 | 2024-02-21 | NCR | Not Required | 2024-03-02 | Daytime | 35 | MAN | 3456691 | Complete | Photos Missing | Stan | 2024-03-07 | Not Submitted | No | Active | 2024-04-10 | 111110 | Re-Imaging | Network Upgrade
Order Accuracy | 6835 | 1017 S 1150 E | Eden | ID | 757 | BOISE ID | Joe Morian | Nick Rice |  |  | Willie, Daniel L. | 2022-09-15 | 2023-01-24 | Under Construction | Comcast | Shipped | 8 | 13 | 15 | 16 | 2025-10-22 | 8928 | 9876 | 2024-03-26 | NCR | Contact Complete [31/Oct] | 2024-04-05 | Overnight | 36 | PAN | 3456702 | Complete with Issues | Not Received | Anderson | 2024-04-10 | Copy Requested | Yes | Active | 2024-05-14 | 122221 | Memory | Network Upgrade
Order Accuracy | 6794 | 5903 Roswell Road | Sandy Springs | GA | 524 | ATLANTA GA | Michael Landru | Jesse Culbertson | RED ARCHITECTS |  | SRI OPERATING COMPANY | 2022-10-04 | 2023-02-16 | Under Construction | Comcast | Order Approved | 9 | 15 | 17 | 18 | 2026-09-24 | 10015 | 10987 | 2024-04-29 | NCR | Not Required | 2024-05-09 | Overnight | 37 | RAN | 3456713 | Not completed | Complete | Ellsworth Sheldon | 2024-05-14 | Submitted | Yes | Active | 2024-06-17 | 133332 | Re-Imaging | Network Upgrade
Order Accuracy | 6946 | 302 S Service Rd E | Sullivan | MO | 609 | ST. LOUIS MO | Charles DeFiglio | Kevin Dalpiaz |  |  | JACOB STAUFFER | 2023-02-09 | 2023-02-20 | Under Construction | Comcast | Shipped | 10 | 17 | 19 | 20 | 2027-08-27 | 11102 | 12098 | 2024-06-02 | NCR | Contact Complete [31/Nov] | 2024-06-12 | Overnight | 38 | HAN | 3456724 | Pending document | Photos Missing | Terrance Gaines | 2024-06-17 | Not Submitted | Yes | Active | 2024-07-21 | 144443 | Memory | Network Upgrade
Order Accuracy | 6975 | 3004 I-30 | Greenville | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  |  | Butt, Tarik | 2022-03-27 | 2023-03-06 | Under Construction | Comcast | Order Approved | 11 | 19 | 21 | 22 | 2028-07-29 | 12189 | 13209 | 2024-07-06 | NCR | Not Required | 2024-07-16 | Overnight | 39 | KAN | 3456735 | Complete | Photos Missing | Ellsworth Sheldon | 2024-07-21 | Submitted | N/A | Issues | 2024-08-24 | 155554 | Re-Imaging | Network Upgrade
Order Accuracy | 6762 | 524 TRIMBLE PLAZA SOUTHEAST | Leesburg | VA | 511 | WASHINGTON DC | Charles DeFiglio | Kevin Dalpiaz |  | Todd Wekenborg | BHAVESH CHANIYARA | 2022-04-20 | 2023-03-06 | Under Construction | Comcast | Pending delivery date | 12 | 21 | 23 | 24 | 2029-07-01 | 13276 | 14320 | 2024-08-09 | NCR | Contact Complete [31/Aug] | 2024-08-19 | Daytime | 33 | SAN | 3456669 | Not completed | Not Received | Stan | 2024-08-24 | Not Submitted | Yes | Issues | 2024-09-27 | 88888 | Re-Imaging | Network Upgrade
Order Accuracy | 6963 | 4601-4613 Gus Thomasson Road | Mesquite | TX | 623 | DALLAS-FT WORTH TX | Jon Brannin | Nick Rice |  | Linda Wiseley | BARTON, THELMA | 2022-08-08 | 2023-03-06 | Under Construction | Comcast | Order Pending FEE Approval | 13 | 23 | 25 | 26 | 2030-06-03 | 14363 | 15431 | 2024-09-12 | NCR | Contact Complete [11/Aug] | 2024-09-22 | Daytime | 34 | GAN | 3456680 | Pending document | Complete | Terrance Gaines | 2024-09-27 | Submitted | No | Active | 2024-10-31 | 99999 | Memory | Network Upgrade